Project Title:	2022 SVTGBI Test Development and Psychometric Services

Inteleos Staff Leads: Cynthia Carr (ARDMS Test Development Manager), Belinda Brunner (Director, Testing), Sarah Pelter (Director, Psychometric Services)

SVTGBI Lead: Emma Waldegrave, President

Program:  The Society for Vascular Technology of Great Britain and Ireland (SVTGBI)

Inteleos and SVTGBI are parties to that certain Memorandum of Understanding (MOU) dated 01/01/2021. The terms and conditions of the MOU are hereby incorporated into this Statement of Work.

SOW # 02

1. Term:  The term of this Agreement shall be from 01/01/2022 – 12/31/2022.

2.  Authority: All work must be agreed upon by Inteleos staff and SVTGBI.

3.  Resources: The designated testing and psychometric services staff will be available to assist and to answer questions.

Inteleos will:

- Assume all costs associated with developing and delivering the SVT Tech and SVT Physics examinations, including the cost of item developing workshops (inclusive of personnel expenses).

- Realize all revenues associated with the SVT Tech and SVT Physics examinations (test-taker fees).

- Realise all revenues associated with the SVT Tech and SVT Physics practice examinations (purchase fees)

SVTGBI will:

- Assume all costs associated with the development education and training material.

- Assume all revenues associated with the education and training material (regardless of its relation to the assessment).

- Assume all costs associated with the development and administration of the SVT practical assessment.

- Assume all revenue associated with the administration of the SVT practical assessment.

4. Deliverables and Timeline:

| ACTIVITY | DELIVERABLE | DUE DATE | PARTY RESPONSIBLE |
| --- | --- | --- | --- |
| Conference calls and communication with staff and SVTGBI members. Identify appropriate subject matter experts (SMEs) to assist in test development activities (item writing, item review, standard setting, practice analysis, etc.) Facilitate remote item writing efforts as needed to address deficits within the item bank. Identify marketing and communication opportunities for SVTGBI examination offerings SVTGBI review of POCUS Content within PCA Create practice examinations for SVT-Tech and SVT-Physics Evaluate methods for review and updating of content outline for SVT Tech and Physics Approve method for content outline updates Review of current SVTGBI practical examination | Leadership participation in scheduled quarterly conference calls; Participation of the Education committee representatives in ongoing communication and conference calls with EPM. Both parties will agree on the skills and demographics of the subject matter expert required (e.g., certification(s) held, geographic location, practice area, etc.) Inteleos will provide a statement of service for the subject matter experts to SVTGBI SVTGBI will return signed statement of service Both parties will agree on areas of need for the item banks. Inteleos will develop item writing projects/assignments for review and approval of SVTGBI. Inteleos to develop and execute communication and marketing plan for SVTGBI examinations; including potential practice examinations. Inteleos staff will provide access to SVTGBI leadership to review POCUS modules in relevant content areas Develop one practice examination form for each SVTGBI examination. SVTGBI responsible for identifying SMEs to write items where necessary. Inteleos will facilitate remote item writing efforts to complete the practice exam forms. Inteleos staff leads will propose options (in writing) for completing content outline review and updating for both exams. This proposal will include proposed timeline and project plan. SVTGBI could engage with upcoming item generation technology through AI. SVTGBI will review proposal and select method for conducting content outline review and updating. SVTGBI allow Inteleos to review current practical assessments and associated materials for the purpose of learning and potential collaboration. | Ongoing Ongoing Ongoing Ongoing Q2 Q2/Q3 2022 Q4 2022 Q4 2022 Q3 2022 | Inteleos/SVTGBI leadership; EPM and Education Committee SVTGBI/Inteleos Inteleos/SVTGBI Inteleos/SVTGBI Inteleos/SVTGBI SVTGBI/Inteleos Inteleos SVTGBI SVTGBI/Inteleos |

In Witness Whereof, the parties have executed this SOW on the day hereinbefore set forth.

SVTGBI:						Inteleos, Inc.

_________________________date_________	__________________________date________

Print Name:						Print Name and Title

______________________________________	__________________________________